## Sheet1
Task Number | Task | Sub Task | Description | Resolution
1 | Milestone 1 | Workload Automation | Building an automated workload capable of running realistic transactions on a database, on a schedule. | N/A
2 | Milestone 1 | Extract system metrics | Extraction of v$ metrics, AWR reports, etc.. | N/A
3 | Milestone 1 | Feature selection (Peak Load) | Identify useful features used for peak load detection (identify points in time when database is at it's lowest/highest activity) | N/A
4 | Milestone 1 | Training + Testing (Peak Load Model Development) | Training + Testing of Peak Load Model | N/A
5 | Milestone 1 | Peak Load Model Evaluation | Evaluation + Interpretation of results | N/A
6 | Milestone 1 | Top SQL Retrieval | Identification of top SQL, dependent of time window | N/A
7 | Milestone 1 | Feature extraction (SQL Entity Breakdown) | Logic capable of breaking down an sql into schema entities eligable for statistics collection | N/A
8 | Milestone 1 | Feature selection (Statistic Prioritization) | Which type of statistic gathering will be prioritized, and which schema entity will be priotirized | N/A
9 | Milestone 1 | Training + Testing (Optimizer Stats Priority Model Development) | Training + Testing of Optimizer Stats Priority Model | N/A
10 | Milestone 1 | Optimizer Stats Priority Model Evaluation | Evaluation + Interpretation of results | N/A
11 | Milestone 1 | Feature Selection (Optimizer Stats Generation Time Estimate Model) | Identify useful features used to predict time (required time windows) taken by particular optimizer stat collection procedures | N/A
12 | Milestone 1 | Training + Testing (Optimizer Stats Generation Time Estimate Model) | Training + Testing of Optimizer Stats Generation Time Estimate | N/A
13 | Milestone 1 | Optimizer Stats Generation Time Estimate Model Evaluation | Evaluation + Interpretation of results | N/A
14 | Milestone 1 | Milestone 1 Testing & Evaluation | Evaluation for milestone 1 components (Peak Load, Stats Priority, Optimizer Stats Generation Time Estimate models) | N/A
15 | Milestone 2 | Workload Automation | Building an automated workload capable of running realistic transaction on a database, on a schedule. | N/A
16 | Milestone 2 | Extract system metrics | Extraction of v$ metrics, AWR reports, etc.. | N/A
17 | Milestone 2 | Feature selection (Peak Load) | Identify useful features used for peak load detection (identify points in time when database is at it's lowest/highest activity) | N/A
18 | Milestone 2 | Training + Testing (Peak Load Model Development) | Training + Testing of Peak Load Model | N/A
19 | Milestone 2 | Peak Load Model Evaluation | Evaluation + Interpretation of results | N/A
20 | Milestone 2 | Top SQL Retrieval | Identification of top SQL, dependent of time window | N/A
21 | Milestone 2 | Feature extraction (SQL Entity Breakdown) | Logic capable of breaking down an sql into schema entities eligable for statistics collection | N/A
22 | Milestone 2 | Feature selection (Statistic Prioritization) | Which type of statistic gathering will be prioritized, and which schema entity will be priotirized | N/A
23 | Milestone 2 | Training + Testing (Optimizer Stats Priority Model Development) | Training + Testing of Optimizer Stats Priority Model | N/A
24 | Milestone 2 | Optimizer Stats Priority Model Evaluation | Evaluation + Interpretation of results | N/A
25 | Milestone 2 | Feature Selection (Optimizer Stats Generation Time Estimate Model) | Identify useful features used to predict time (required time windows) taken by particular optimizer stat collection procedures | N/A
26 | Milestone 2 | Training + Testing (Optimizer Stats Generation Time Estimate Model) | Training + Testing of Optimizer Stats Generation Time Estimate | N/A
27 | Milestone 2 | Optimizer Stats Generation Time Estimate Model Evaluation | Evaluation + Interpretation of results | N/A
28 | Milestone 2 | Milestone 2 Testing & Evaluation | Evaluation for milestone 2 components (Peak Load, Stats Priority, Optimizer Stats Generation Time Estimate models) | N/A
29 | Milestone 3 | Write-Up | Compile Write Up | N/A
Not Started
Running
Under Development
Blocked
Done